## Use Case Template
Project Title: ASP.NET Minesweeper Release #: 1 Sprint #: 1
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
1 | Preset game | User | Select a game size | to start a game | 1 | MT
| Custom game | User | Set a custom game size | to have variety | 1
3 | Play game | User | Lose when a mine is clicked | to end the game | 1
4 | Play game | User | win when all safe spaces are cleared | to end the game | 1
5 | Play game | User | check a space | to progress the game | 1
6 | Play game | User | Enable flagging of spaces. A flagged space cannot be checked without un-flagging. | prevent the user from accidentally clicking a known mine | 1
Milestone 2
7 | Login | User | Sign into the application | I could play a game of minesweeper | 1
8 | Registration | User | Create an account | I could log in and play Minesweeper | 1
9 | Edit information | user | edit / update information | any information can be updated accordingly | 1
10 | Change theme colors | User | change the color of the board / theme | to have better customization / legibility throughout the app | 10
11 | Page Navigation | User | navigate through the application seamlessly | to show pages are functional, show implemented css, understanding of Razor, and that it works | 10
Milestone 3
12 | User Homepage | user | direct users to their home page once signed in | to show that our login validation works | 2
13 | Game Board Render | user | allow users to play minesweeper | we can demonstrate our game func | 10
14 | Registration Requierments | user / admin | implement field requierments during reg | no empty fields are valid | 1 | MT
15 | Login Requierments | user / admin | implement field requierments during login | a user must input their info to login | 2 | CL
16 | Log out | user / admin | users are able to log out and return to index | we can end the session / log out | 3 | CL
Milestone 4
17 | Asychronous gameboard | User | play without reloading the entire page | I can do multiple moves without wait time. | 6 | Connor
18 | Game Timer | User | keep track of game length | I can compare my performance | 4 | CL
19 | Highscores | User | save my game times for boards | I can compare my performance | 3 | MT
20 | Flagging Mines | User | flag a mine | mines can be marked some way | 6 | MT
21 | Auto-save | User | have the game save automatically every few seconds | I don't have to manually save the game | 4 | CL
22 | Manual save | User | save the game | I can continue later | 3 | MT
23 | Load game | User | load a game | I can continue later | 3 | CL
Milestone 5
22 | Save Game | User | save my game to play it at a later time | I can continue my game later | 3 | CL
23 | Load game | User | load my saved game | I can continue and win! | 3 | CL
24 | Delete save file | user | delete any old saved game | I can play a new game | 2 | MT
25 | View highscores | user / admin | see the highscore page for each difficulty | I can see who's better or worse | 2 | CL
Milestone 6 (Final)
26 | Home Button | user | return to the user home page | I can exit the game page | 1.5 | MT
27 | Better looking Buttons | user / admin | Clicking on a button rather than a link | the user can easily find what to click | 1 | CL
28 | Security Filter | admin | Redirect non users to public pages | they cannot access proteced pages | 3 | MT / CL